# Graduation Project Management Plan

SportSphere — Integrated Sports Networking and Talent Development Platform

Sara Abdulwahab, Project Manager / Team Lead

16 October 2026

# Contents

- Project Overview and Charter

- Scope and Requirements Management

- Deliverables and Acceptance Criteria

- Work Breakdown Structure (WBS)

- Schedule and Milestones

- Team Structure and Responsibilities

- Communication and Meeting Plan

- Risk Management and Mitigation

- Issue, Assumption, Dependency, and Decision Logs

- Quality Management and Testing

- Resource and Budget Management

- Change Control

- Document and Information Management

- Progress Monitoring and Reporting

- Stakeholder and User Engagement

- Ethics, Data, and Responsible Practice

- Final Report and Presentation Checklist

- Project Closure and Lessons Learned

- Weekly Team Action Tracker

- Approval and Commitment
Appendix A — Recommended Submission Package
Appendix B — One-Page Project Snapshot
Appendix C — Source Register and Traceability Notes

# Document Control

| Item | Details |
| --- | --- |
| Project title | SportSphere — Integrated Sports Networking and Talent Development Platform |
| Team / cohort | SportSphere Graduation Project Team; cohort details were not stated in the supplied source documents |
| Project Manager / Team Lead | Sara Abdulwahab |
| Supervisor / Official Approver | Eng./Dr. Yasmain ElSharakwy |
| Document name | Project_Management_Graduation_Project_Management_Plan |
| Version and date | v1.0 — 16 October 2026 |
| Document status | Consolidated planning baseline submitted for supervisor review; not yet formally approved |
| Proposed project start | Monday, 19 October 2026 (planning assumption) |
| Proposed project finish | Sunday, 10 January 2027 (planning assumption) |
| Duration | 12 weeks, W1–W12, with W11 designated as the contingency/buffer week |
| Delivery platform | Responsive, mobile-first web application; no native Android or iOS application in this phase |
| Team size | 6 members, including the Project Manager |
| Planning effort assumption | Approximately 8–10 hours per member per week, subject to confirmation |
| Demonstration environment | Local demonstration environment; cloud hosting is optional |

## Purpose and Use of This Plan

This document consolidates the project-management template, SportSphere planning baseline, and AthleteConnect requirements-gathering material into one working plan for SportSphere. It covers initiation, requirements, scope, delivery planning, execution controls, verification, responsible practice, final submission, and closure. It is to be maintained as a live baseline: progress, decisions, risks, issue statuses, actual costs, and measured results must be updated as evidence becomes available.

## Baseline Interpretation and Reconciliation Notes

| Topic | Consolidated treatment in this plan |
| --- | --- |
| Project and requirements-document names | SportSphere is the project title. “AthleteConnect” is the title used by the supplied requirements-gathering document; its relevant stakeholder, story, use-case, and requirement content is retained and incorporated under SportSphere. |
| Supervisor | Eng./Dr. Yasmain ElSharakwy is the supervisor and official approver throughout this plan, as specified for this consolidation. The planning PDF itself marked the supervisor as “to be confirmed”; the named supervisor and approval authority must still formally sign this plan. |
| Calendar dates | The source baseline specifies W1–W12 but does not give approved calendar dates. The dates in this plan are a consistent proposed schedule beginning 19 October 2026 and ending 10 January 2027. They become the approved calendar baseline only after supervisor confirmation. |
| Role model | The SportSphere plan uses five canonical system-role groups: Athlete, Club, Coach/Staff, Health & Performance Professional, and Admin. The requirements document also names Scouts and Sponsors as stakeholder personas/account types. For the initial design, scout functions are mapped to Coach/Staff permissions and sponsor-specific behaviour is treated as a specialist persona/capability, not a separate sixth top-level role, unless Eng./Dr. Yasmain ElSharakwy approves a change in Week 2. |
| Video feature | The requirements-gathering document lists sports-video upload/playback as a Must-have, while the SportSphere scope baseline does not list it among the core Must-have features. To preserve the source requirement without silently dropping it, FR-06 remains recorded as Must-have in the traceability matrix and is subject to a Week 2 feasibility and acceptance review. Video analysis is explicitly out of scope. If upload/playback cannot be completed safely in the schedule, any reprioritisation requires approval through change control. |
| Networking and notifications | The requirements document groups connection requests and direct messaging in FR-12 as Must-have and lists notifications as Should-have. The SportSphere baseline puts connection requests in Should-have and in-app messaging/email notifications in Could-have. The delivery baseline therefore separates connection requests (Should) from direct messaging (Could) and treats email notifications as Could; this conflict must be confirmed at the scope-baseline gate. |
| Responsive web and mobile app | Responsive web layout is Must-have under SportSphere. FR-19 is therefore treated as Must for responsive web; the native mobile app mentioned as a later phase remains out of scope. |
| Team member names | The source files identify Sara Abdulwahab and assign Members 2–6 by role, but do not provide the other members’ names. The role labels “Team Member 2” through “Team Member 6” are used rather than inventing personal names. Named assignments must be entered by the team at kickoff. |
| Budget and actual results | No approved monetary budget or measured test results were supplied. This plan uses free-tier tools and a local demo as the cost-control baseline. KPI figures are targets, not achievements. Actual cost and test results must be recorded when measured. |

# 1. Project Overview and Charter

## 1.1 Project Charter

| Charter item | SportSphere response |
| --- | --- |
| Project title | SportSphere — Integrated Sports Networking and Talent Development Platform |
| Problem / opportunity | Athletes and sports professionals commonly discover suitable clubs, sports opportunities, specialists, and contacts through fragmented sources such as social media, club websites, personal networks, and separate directories. Fragmentation makes relevant profiles difficult to compare and opportunities harder to discover. The project will validate this problem through user feedback rather than claim that its scale has already been measured. |
| Target users / beneficiaries | Athletes; sports clubs and academies; coaches and technical staff; scouts/recruitment personnel; health and performance professionals such as physiotherapists, rehabilitation specialists, fitness trainers, nutritionists, psychologists, and sports scientists; sponsors as a specialist persona; platform administrators; and, indirectly, parents/guardians of under-18 athletes. |
| Project purpose | Design, develop, and evaluate a responsive academic prototype that centralises sports profiles, profile discovery, opportunity listings, and basic professional networking. |
| SMART objective | By the end of Week 12 (proposed 10 January 2027), deliver and demonstrate a responsive SportSphere MVP covering the approved Must-have requirements, with traceable requirements and test evidence; achieve at least a 95% functional test pass rate, zero unresolved critical defects, 100% completion of Must-have responsive checks across mobile/tablet/desktop, and a documented usability evaluation targeting 10–15 participants where available. Any unmet target or approved exception will be reported honestly. |
| Proposed solution | A mobile-first web application in which users register and manage role-appropriate profiles, search athletes and professionals, discover trial/recruitment/training opportunities, and use approved networking functions. The system includes basic administrator moderation and verification labels. It is a professional networking prototype, not a medical service or a guaranteed recruitment channel. |
| Expected benefits | Athletes gain an organised place to present experience, skills, achievements, and sports information. Clubs and talent seekers gain a more structured way to discover profiles. Professionals can present specialties. The team gains an evidence-based prototype and documented basis for future enhancements. These are expected benefits, not proven outcomes. |
| Success criteria | Approved baseline completed; D1–D6 delivered and reviewed; approved core workflows demonstrable in the local environment; requirement IDs traceable to verification evidence; functional test pass rate at least 95%; zero unresolved critical defects; all Must-have responsive pages checked at three screen sizes; feedback and limitations documented; final report and demonstration submitted by Week 12. |
| Constraints | Fixed 12-week academic window; six-person team; estimated 8–10 hours per member weekly; technology selection based on team skills; no approved cash budget in supplied sources; supervisor approval required for baseline changes; native mobile applications and commercial-scale deployment excluded. |
| Assumptions | A local demo environment is available; sample/test accounts and synthetic data can be used; cloud hosting is optional; the team can access suitable development devices and free-tier tools; research participants can be approached ethically where available; supervisor reviews can occur every one or two weeks. Each assumption is tracked in Section 9. |

## 1.2 SMART Objective Check

| Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- |
| Build a responsive web MVP for sports profiles, discovery, opportunity listings, and basic networking. | At least 95% functional test pass rate; zero open critical defects; 100% of agreed Must-have requirements either pass or have a supervisor-approved exception; usability target of 10–15 participants where available. | Six roles are allocated, development is split into three sprints, Must-have work is protected, Could-have work is deferred first, and a buffer week is reserved. | Addresses fragmented sports networking and discovery while keeping medical services, predictive AI, payments, and native apps outside the MVP. | Proposed Week 12 finish: 10 January 2027, subject to approval of the proposed calendar dates. |

## 1.3 Project Objectives and Measures

| ID | Objective | Measure of success | Owner |
| --- | --- | --- | --- |
| O1 | Provide role-based registration, login, and profile management. | Each approved canonical role can complete its allowed sign-up/login/profile workflow in test cases. | Backend Developer; QA Lead verifies |
| O2 | Enable clubs, coaches, and scouts to discover athletes. | Search by sport, position, location and other approved attributes returns expected results in predefined scenarios. | Frontend and Backend Developers |
| O3 | Provide searchable directories for health and performance professionals. | Specialty and location filters work against seeded test records. | Development Team |
| O4 | Enable clubs/coaches to publish sports opportunities. | Listing can be created, edited, viewed, and closed; athletes can find it and express interest where that Should-have function is approved. | Development Team |
| O5 | Provide a safe basic networking workflow. | Connection requests can be sent and accepted/declined if retained in the approved Should-have scope; direct messaging remains Could-have. | Development Team |
| O6 | Protect user information, especially under-18 athletes. | Privacy defaults, contact-detail restrictions, role permissions, and consent notices pass the security/privacy checklist. | Backend Developer; QA Lead verifies |
| O7 | Evaluate the academic prototype with structured testing and feedback. | Test report records executed tests, pass/fail results, defects, user feedback, limitations, and unverified targets. | QA Lead and Research/Documentation Lead |

# 2. Scope and Requirements Management

## 2.1 In-Scope and Out-of-Scope Baseline

| In scope | Out of scope |
| --- | --- |
| Responsive mobile-first web application and local demonstration build. | Native Android and iOS applications. |
| Registration, email verification, login, password reset, and role-based access for the approved role model. | Full commercial-scale deployment or guaranteed production-level capacity. |
| Athlete profiles with sport, position, experience, achievements, statistics, skills, and certifications according to priority. | Electronic medical records, diagnoses, prescriptions, treatment recommendations, emergency medical services, or clinical monitoring. |
| Club, coach/staff, and health/performance professional profiles with a shared specialist-field approach. | AI-based athlete-performance or medical-outcome prediction and automated talent selection. |
| Search/filtering by sport, position, location, specialty, and approved athlete attributes. | Video analysis tools or advanced performance-video analysis. |
| Listings for trials, recruitment, vacancies, training, and approved opportunity categories. | Payments, payroll, insurance, automated contracts, or paid subscriptions. |
| Basic privacy controls; private-by-default treatment of under-18 athletes; hidden contact details; verification labels. | Integrations with hospitals, wearables, external recruitment systems, or club-management systems. |
| Basic administration: verification status, report review, moderation, and account suspension. | Guaranteed recruitment, employment, sponsorship, or professional contracts. |
| Approved basic connections, bookmarks, expressions of interest, or sponsor capabilities according to the final MoSCoW decision. | Real-time clinical or emergency workflows; full appointment-management or facility-booking system. |
| Functional/responsive/security testing, documentation, final report, presentation, and handover. | Commercial integrations or new features not reviewed through change control. |

## 2.2 MoSCoW Rules

| Priority | Definition for SportSphere |
| --- | --- |
| Must | Required for the academic MVP unless a formal change is approved. Protect these features against time pressure. |
| Should | Important and intended if the Must baseline and quality gates remain on schedule. Connection requests are the first candidate for downgrade if Sprint 3 slips, subject to supervisor notification. |
| Could | Optional enhancements. Defer these first when schedule, integration, security, or quality is at risk. Direct messaging, email notifications, profile photo upload, and the admin dashboard expansion are examples. |
| Won’t have in this phase | Explicitly excluded from this release, including native apps, advanced video analysis, medical records, payments, and AI prediction. |

## 2.3 Functional Requirements Traceability Matrix

The “baseline priority” column applies the SportSphere scope plan as the delivery control. Where the requirements document assigns a different priority, the variance is stated so the supervisor can approve the final baseline. The requirement IDs are preserved as supplied; no FR-20 is defined in the source material.

| ID | Functional requirement | Source priority / source note | Proposed baseline priority | Verification method and acceptance evidence | Primary owner |
| --- | --- | --- | --- | --- | --- |
| FR-01 | Register and log in using email, with email verification and password reset using an expiring reset link. | Must-have in requirements document. | Must | Positive/negative sign-up and login tests; unverified-email test; reset-token expiry test; evidence in test log. | Backend Developer; QA Lead verifies |
| FR-02 | Provide role-based accounts for athlete, coach, club, scout, sponsor, and administrator personas. | Must-have; requirements document lists six account/persona types, while SportSphere plan specifies five canonical role groups. | Must; five canonical system roles with scout and sponsor capabilities mapped as specialist permissions unless a sixth top-level role is approved. | Test each canonical role and permission boundary; verify unauthorised actions are denied. Record supervisor decision on role mapping. | Backend Developer; PM manages decision |
| FR-03 | Create and edit an athlete profile with personal details, sport, position, and experience. | Must-have. | Must | Create/edit/save/read tests with required-field validation and profile visibility checks. | Frontend and Backend Developers |
| FR-04 | Record achievements, awards, and performance statistics. | Must-have. | Must | Add/edit/display validated test values; verify empty and invalid values are handled. | Development Team |
| FR-05 | List skills and certifications. | Should-have in requirements document. | Should | Add, edit, and display skills/certification fields; verify labels do not imply unearned verification. | Frontend Developer; Business Analyst defines fields |
| FR-06 | Upload, play, and manage sports videos on an athlete profile. | Listed in the requirements document’s Must-have group; not separately itemised as Must in SportSphere’s scope table. | Must pending Week 2 feasibility confirmation; limit to straightforward profile video upload/playback, with no analysis tools. Any downgrade requires supervisor approval. | Upload/manage an approved test video; playback begins within five seconds under the defined test setup if this feature is approved; test media rights and file limits. | Backend Developer; QA Lead verifies |
| FR-07 | Set profile visibility and privacy controls. | Must-have in requirements document; aligns with SportSphere privacy baseline. | Must | Verify public/private settings, default privacy for under-18 profiles, and hiding of contact details. | Backend Developer; QA Lead verifies |
| FR-08 | Search and filter athletes by sport, position, location, age group, and statistics. | Must-have. | Must | Execute predefined search scenarios and verify filters, expected matches, empty results, and response-time target. | Backend and Frontend Developers |
| FR-09 | Search and filter sports opportunities such as trials, vacancies, and sponsorship opportunities. | Must-have. | Must for trial/recruitment/training listings; sponsor-specific offer workflows remain Should. | Test each approved listing category, filters, and result accuracy using synthetic records. | Frontend and Backend Developers |
| FR-10 | Allow clubs and coaches to create, edit, and close opportunity listings. | Must-have. | Must | Create/edit/close tests; verify closed listings no longer appear as open opportunities. | Backend Developer; Frontend Developer |
| FR-11 | Allow athletes to apply to an opportunity and track application status. | Should-have. | Should | Submit an application, view its status, and test allowed status transitions. | Development Team |
| FR-12 | Support networking through connection requests and direct messages between users. | Requirements document groups both as Must-have; SportSphere places connection requests in Should and messaging in Could. | Split baseline: connection requests = Should; direct messages = Could and not required for core acceptance. | Test request send/accept/decline if included. If messaging is implemented, test delivery and access isolation; otherwise document it as deferred. | Frontend and Backend Developers; PM confirms priority |
| FR-13 | Provide notifications through in-app alerts and email. | Should-have in requirements document; SportSphere lists email notifications as Could. | In-app alerts for retained workflows = Should where needed; email notifications = Could. | Trigger applicable alert; verify recipient, content, and no exposure of hidden private information. Email path may be deferred. | Backend Developer; QA Lead verifies |
| FR-14 | Shortlist athletes and compare two or more profiles side by side. | Should-have. | Should if Must baseline is stable; reduce to bookmarking if time is constrained. | Add at least two test profiles to a shortlist and verify the agreed comparison fields. | Frontend Developer |
| FR-15 | Allow sponsors to browse athletes and send sponsorship offers that an athlete can accept or decline. | Should-have; sponsor is a persona in requirements analysis, not one of SportSphere’s five canonical system-role groups. | Should; specialist permissions must be agreed in Week 2. No payment or contract automation. | Test offer creation, recipient visibility, accept/decline status, and permission boundaries if included; otherwise record approved deferral. | Backend Developer; PM owns role decision |
| FR-16 | Verify accounts, review flagged content, and suspend users. | Must-have. | Must (basic administration only) | Admin workflow tests for verification label, report review, moderation action, and suspension; preserve audit evidence where supported. | Backend Developer; QA Lead verifies |
| FR-17 | Provide a dashboard of users, activity, and opportunities. | Could-have. | Could | If implemented, verify counts against seeded test data; otherwise record as deferred. | Frontend Developer |
| FR-18 | Provide Arabic and English interface options. | Could-have. | Could | If implemented, switch language and inspect key navigation/form labels; otherwise document future phase. | UI/UX Designer and Frontend Developer |
| FR-19 | Provide a responsive web interface; native mobile app may be a later phase. | Should-have in requirements document; SportSphere makes responsive layout Must. | Must for responsive web; native application remains out of scope. | Test approved Must-have pages at mobile, tablet, and desktop widths in at least two browsers; record screenshots/checklist. | UI/UX Designer; Frontend Developer; QA Lead verifies |

## 2.4 Non-Functional Requirements Traceability Matrix

| ID | Category | Requirement and measurable target | Baseline treatment | Verification method and acceptance evidence | Owner |
| --- | --- | --- | --- | --- | --- |
| NFR-01 | Performance | Pages load in under 3 seconds on a standard broadband connection. | Target for key MVP pages. | Measure representative pages using a documented test setup; report median and outliers. | QA Lead / Frontend Developer |
| NFR-02 | Performance | Search returns results in under 2 seconds for 95% of queries. | Target for the agreed seed-data test set. | Time a predefined set of search queries and calculate percentage under two seconds. | QA Lead / Backend Developer |
| NFR-03 | Performance | Video playback begins within 5 seconds, with adaptive streaming. | Applies if FR-06 video playback is retained; advanced video analysis remains excluded. | Time playback from the defined test network and media set; document if adaptive streaming is not supported by the local demo. | Backend Developer / QA Lead |
| NFR-04 | Scalability | Supports 10,000 concurrent users without redesign. | Long-term architecture target; not a validated acceptance claim for a local academic prototype. | Architecture/design review; only claim load-test compliance if an approved load test is actually performed. | Technical Lead role: Backend Developer |
| NFR-05 | Security | Passwords are hashed, traffic uses HTTPS, and data is encrypted at rest. | Required security design; HTTPS/encryption acceptance depends on whether the demo is hosted and the storage stack supports it. No real sensitive data. | Inspect password storage, deployment configuration, transport settings where applicable, and security checklist. | Backend Developer / QA Lead |
| NFR-06 | Security | Role-based permissions are enforced on every request. | Must. | Attempt authorised and unauthorised requests for each role; record pass/fail. | Backend Developer / QA Lead |
| NFR-07 | Privacy | Record user consent; obtain guardian consent for under-18 athletes; allow users to export or delete their data. | Must safeguard; use test-only data and implement the feasible MVP controls. | Inspect consent flow, under-18 default privacy, contact restrictions, and export/delete workflow or documented accountable deletion procedure. | Business Analyst / Backend Developer |
| NFR-08 | Usability | A first-time athlete can complete a profile in under 15 minutes without help. | Usability target. | Observe representative participants; time task and record completion/help required. | Research/Documentation Lead / QA Lead |
| NFR-09 | Usability/accessibility | Responsive on phone, tablet, and desktop; WCAG 2.1 AA accessibility target. | Responsive layout is Must; accessibility is checked with a documented review, without claiming formal certification. | Screen-size checks, keyboard/navigation review, labels/contrast checks, and accessibility checklist. | UI/UX Designer / QA Lead |
| NFR-10 | Reliability | 99.5% monthly uptime. | Only measurable for a hosted pilot with a defined monitoring period; not claimed for an unmonitored local demo. | Monitor availability during an approved hosted pilot and include duration/sample size in the report. | Project Manager / Backend Developer |
| NFR-11 | Reliability | Daily backups and recovery within 4 hours. | Backup and recovery procedure must be documented; recovery target to be tested where environment permits. | Confirm backup cadence and perform a restore/recovery drill; report elapsed time. | Backend Developer |
| NFR-12 | Maintainability | Modular code, documented APIs, and 70% automated test coverage. | Target where the selected stack and test setup support measurement. | Code review, API documentation check, and automated coverage report. | Backend Developer / QA Lead |
| NFR-13 | Compatibility | Works across the latest two versions of Chrome, Safari, Edge, and Firefox. | Full target preserved; minimum SportSphere scope check is two browsers, with all four browser families tested if devices/time permit. | Record browser/version matrix and defects; explicitly list any untested combinations. | QA Lead / Frontend Developer |

## 2.5 User Stories and Acceptance Criteria

| ID | Persona | User story | Acceptance criterion from the requirements source | Planned treatment |
| --- | --- | --- | --- | --- |
| US-01 | Athlete | I want a profile with achievements, statistics, skills, and experience so I can present my abilities credibly. | The profile saves and displays all agreed sections. | Core profile Must; skills/certifications priority follows FR-05. |
| US-02 | Athlete | I want to upload and organise sports videos so coaches and scouts can see me perform. | Video plays on the profile within 5 seconds. | FR-06/NFR-03; confirm feasibility in Week 2; no video analysis. |
| US-03 | Athlete | I want to search and filter sports opportunities so I can find relevant trials and openings. | Results filter by sport, location, and level. | Must for opportunity discovery. |
| US-04 | Athlete | I want to message coaches, clubs, scouts, and sponsors so I can start career conversations. | Message is delivered and a notification is sent. | Direct messaging/notification split is Could pending approved scope. |
| US-05 | Coach | I want to search athletes by sport, position, and statistics so I can find players for my team. | Search returns ranked/filterable results. | Must for search and filters; ranking beyond clear deterministic filtering is not promised unless specified. |
| US-06 | Club | I want to post trials and vacancies so I can attract suitable athletes. | A posted opportunity appears in athlete search. | Must. |
| US-07 | Scout | I want to shortlist athletes and compare their profiles so I can evaluate talent in one place. | Shortlist compares two or more athletes side by side. | Should; scout permissions mapped to Coach/Staff unless approved otherwise. |
| US-08 | Sponsor | I want to browse athletes and send sponsorship offers so I can partner with promising talent. | Offer reaches the athlete and can be accepted or declined. | Should; no payments or contract automation. |
| US-09 | Administrator | I want to verify accounts and moderate content so the platform stays reliable and safe. | Flagged content can be reviewed and actioned in the admin panel. | Must, basic administration only. |
| US-10 | Any user | I want to register, log in, and reset my password securely so my account is protected. | Login works with a verified email and the reset link expires. | Must. |

## 2.6 Use Cases

| ID | Primary actor | Main flow | Expected outcome | Priority / related requirements |
| --- | --- | --- | --- | --- |
| UC-01 — Create athlete profile | Athlete | Register and verify email; enter personal/sports details; add statistics and approved media; save and publish according to privacy settings. | Profile is saved and visible only to the audience allowed by its privacy setting. | Must; FR-01, FR-03, FR-04, FR-07; FR-06 subject to Week 2 confirmation. |
| UC-02 — Discover and connect | Athlete | Search opportunities; open a listing; send a connection request or use an approved contact function. | Contact request is recorded and its status is visible. | Search Must; connection request Should; direct messaging Could. |
| UC-03 — Search and evaluate athletes | Coach / scout / club | Apply filters; view profile details and approved videos; shortlist profiles; initiate allowed contact. | Search results and shortlist support talent discovery. | Search Must; shortlist/compare Should; FR-08, FR-12, FR-14. |
| UC-04 — Post an opportunity | Club / coach | Create a listing with requirements and deadline; publish; edit or close it; review any applicants if application tracking is in scope. | Listing appears in discovery and status is managed correctly. | Listing Must; application tracking Should; FR-09–FR-11. |
| UC-05 — Propose sponsorship | Sponsor persona | Browse athletes; review approved public information; send offer; track athlete response. | Offer status is visible to authorised parties. | Should; FR-15; no payments or automated contracts. |
| UC-06 — Moderate platform | Administrator | Review flagged profile/content; verify account status or suspend account; record action. | Account/content is reviewed and an appropriate moderation action is applied. | Must; FR-16. |

## 2.7 Scope Control

No new feature begins implementation merely because a stakeholder requests it. The Project Manager records the request, assesses impact on scope, milestones, person-hours, costs, quality, privacy, security, and risks, and submits it to Eng./Dr. Yasmain ElSharakwy. The baseline changes only after approval is recorded. If schedule pressure occurs, Could-have items are removed first, followed by approved Should-have reductions; Must-have quality and privacy controls are protected.

# 3. Deliverables and Acceptance Criteria

| Deliverable | Content | Owner | Planned due | Acceptance criteria / evidence | Approver |
| --- | --- | --- | --- | --- | --- |
| D1 — Project Proposal and Management Plan | Problem, objectives, charter, scope, stakeholders, assumptions, WBS, schedule, team, communication, risk, quality, resource, change, and document controls. | Sara Abdulwahab | End of W2 — 1 November 2026 | All required sections populated; unresolved source conflicts recorded; proposed baseline reviewed and approved. | Eng./Dr. Yasmain ElSharakwy |
| D2 — Requirements Specification | Stakeholder register, US-01–US-10, UC-01–UC-06, FR-01–FR-19, NFR-01–NFR-13, MoSCoW baseline, verification and acceptance criteria. | Team Member 2 — Business Analyst / Documentation Lead | End of W3 — 8 November 2026 | Every source requirement is traceable; priorities and any variances are visible; supervisor decisions on role mapping and FR-06/FR-12/FR-13/FR-19 are logged. | Eng./Dr. Yasmain ElSharakwy |
| D3 — UI/UX Prototype and Data Model | Main screens, role/user journeys, mobile-first layouts, profile and opportunity flows, data model/API contract. | Team Member 3 — UI/UX Designer, supported by Backend Developer | End of W4 — 15 November 2026 | Five canonical role groups and relevant personas represented; primary screens and flows reviewed; phone/tablet/desktop layouts included; data/API contract documented. | Eng./Dr. Yasmain ElSharakwy |
| D4 — Functional SportSphere MVP | Responsive website, accounts, profiles, search/directories, opportunity listings, privacy, verification/moderation, and any approved Should/Could items. | Team Members 4 and 5 — Frontend and Backend Developers | Core Must features by end of W8 — 13 December 2026 | Approved Must features run end-to-end in the local demo or approved host; sample data is clearly synthetic; source code and setup instructions are available; no open critical defect at test gate. | Eng./Dr. Yasmain ElSharakwy |
| D5 — Testing and Evaluation Report | Test cases, pass/fail results, defect log, responsive/security/privacy checks, user feedback, KPI calculations, limitations, and retest evidence. | Team Member 6 — QA / Testing Lead, with Research Lead | End of W10 — 27 December 2026 | Results are reproducible and honest; all critical issues have a disposition; measured results are distinguished from targets and untested assumptions. | Eng./Dr. Yasmain ElSharakwy |
| D6 — Final Report, Presentation, Demonstration and Handover | Final report, slide deck, live or recorded demo, source repository, setup guide, release snapshot, known limitations, closure record, and handover. | Sara Abdulwahab and Team Member 2 — Documentation Lead | End of W12 — 10 January 2027 | Final report matches the actual prototype; demo is rehearsed; backup demo video and local copy work; files are versioned and submitted; supervisor sign-off/feedback is recorded. | Eng./Dr. Yasmain ElSharakwy |

# 4. Work Breakdown Structure (WBS)

The WBS follows the eight work packages in the SportSphere planning source. Work can overlap where dependencies permit, particularly testing and documentation. Estimates are elapsed calendar periods unless described as person-hours.

| WBS | Work package / task | Main activities | Output | Owner | Planned timing / effort |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Initiation and planning | Confirm problem, charter, scope boundaries, MoSCoW, assumptions, stakeholders, roles, initial risks, and governance. | D1 draft and planning baseline | Sara Abdulwahab | W1–W2; approximately 12–16 PM person-hours |
| 1.1 | Define objective and constraints | Write SMART objective, constraints, assumptions, success criteria. | Approved charter content | Sara Abdulwahab | W1; 2–3 days elapsed |
| 1.2 | Identify stakeholders | Capture primary users, sponsor, supervisor, development team, legal/data advisor, regulators, parents/guardians. | Stakeholder register | Team Member 2 | W1; 1–2 days elapsed |
| 1.3 | Baseline scope and risk | Rank features, document exclusions, score R1–R13, define change rules. | MoSCoW baseline and risk register | Sara Abdulwahab | W1–W2; 2–3 days elapsed |
| 2.0 | Requirements analysis | Gather user needs; inspect reference platforms; specify user stories/use cases, FRs/NFRs, priorities, and acceptance criteria. | D2 | Team Member 2 | W2–W3 |
| 2.1 | Review comparable platforms | Review Hudl, Teamworks, and LinkedIn as references for profile organisation, talent discovery, and networking; avoid claiming feature parity. | Competitor/reference summary | Team Member 2 | W2; 2–3 days elapsed |
| 2.2 | Gather and analyse user needs | Interviews, surveys, workshops, and prototype feedback where participants are available; document sample size and limitations. | Findings and needs list | Team Member 2 | W2–W3; 3–4 days elapsed |
| 2.3 | Prioritise and define acceptance | Link FR/NFR/US/UC to acceptance and verification evidence; resolve conflicts with supervisor. | Signed-off requirement baseline | Team Member 2; Sara coordinates | W3; 2–3 days elapsed |
| 3.0 | UI/UX and data design | Design mobile-first screens, user journeys, data model, navigation, role/permission mapping, and API contract. | D3 | Team Member 3 and Team Member 5 | W3–W4 |
| 3.1 | Design key user journeys | Profile creation, search, opportunity publication, connection workflow, moderation. | Wireframes and prototype | Team Member 3 | W3; 2–3 days elapsed |
| 3.2 | Data/API design | Define profile, role, specialty, opportunity, request, report, and verification status fields. | Data model/API contract | Team Member 5 | W3–W4; 2–3 days elapsed |
| 4.0 | User management | Implement registration, email verification, login/reset, profile editing, role permissions, and privacy defaults. | User-management module | Team Members 4 and 5 | W4–W5 |
| 4.1 | Environment/repository | Create repository, branch rules, baseline setup, test environment, and sample data structure. | Reproducible development setup | Team Member 5 | W4; 1–2 days elapsed |
| 4.2 | Frontend profile forms | Implement responsive registration and profile screens with input validation. | Account/profile screens | Team Member 4 | W4–W5; 1–2 weeks |
| 4.3 | Backend account/privacy logic | Implement authentication, permissions, visibility, under-18 defaults, and test-data handling. | Account/profile backend | Team Member 5 | W4–W5; 1–2 weeks |
| 5.0 | Search and directories | Implement search/filtering for athletes, professionals, opportunities, and approved profile attributes. | Search and directory module | Team Members 4 and 5 | W6–W7 |
| 5.1 | Search/filter interface | Build filter controls, result views, empty states, and responsive result cards. | Search UI | Team Member 4 | W6–W7; 1 week |
| 5.2 | Search and listing logic | Implement approved filters, result retrieval, and listing state changes. | Search/query logic | Team Member 5 | W6–W7; 1 week |
| 6.0 | Networking and administration | Implement approved connection-request workflow, basic admin panel, moderation, suspension, and verification labels. | Networking/admin module | Team Members 4 and 5 | W8 |
| 6.1 | Request workflow | Send/accept/decline connection requests if retained in approved Should scope; keep direct messaging behind Could priority. | Request status flow | Team Members 4 and 5 | W8; 2–4 days elapsed |
| 6.2 | Admin and moderation | Flag/review content, set Verified/Unverified, suspend account where authorised. | Basic admin panel | Team Member 5 | W8; 2–4 days elapsed |
| 7.0 | Testing and evaluation | Unit/integration checks, per-sprint verification, system testing, responsive/privacy review, usability feedback, fixes and retesting. | D5 | Team Member 6 | W5–W10; continuous testing, formal system testing W9–W10 |
| 7.1 | Early test design | Define scenarios and test data before features are complete. | Test plan and cases | Team Member 6 | W5; 2–3 days elapsed |
| 7.2 | Regression and integration | Run checks at each sprint; record defects and ownership; retest fixes. | Test/defect logs | Team Member 6 and developers | W5–W10; recurring |
| 7.3 | Usability evaluation | Recruit 10–15 participants where available; run task scenarios and collect survey responses; report non-response as a limitation. | Usability findings | Team Member 2 and Team Member 6 | W9–W10; 2–3 days elapsed |
| 8.0 | Documentation and delivery | Maintain records continuously, finalise report, rehearse demo, prepare backup recording and handover. | D6 | Sara Abdulwahab and Team Member 2 | W1–W12, finalisation W11–W12 |
| 8.1 | Continuous documentation | Capture decisions, risk changes, test outcomes, diagrams, references, and screenshots. | Maintained evidence folder | Team Member 2 | W1–W12; ongoing |
| 8.2 | Final rehearsal and submission | Rehearse with sample accounts; verify local environment and recorded backup; package source/report/slides. | Submitted final package | Sara Abdulwahab | W11–W12; 2–3 days elapsed |

## 4.1 Effort and Ownership Rules

- The team planning envelope is 576–720 person-hours across 6 members over 12 weeks (6 × 8–10 hours × 12 weeks). This is a planning range, not a timesheet result.

- The owner listed for a work package coordinates the output. Contributors must be identified in the task board before work begins.

- Every critical task needs a backup owner. Developers share defect fixing; the QA Lead may assist with frontend tasks during W5–W7 if workload requires it, without independently accepting their own fixes.

- The selected technology stack is confirmed in W2 after comparing team skills, local demo constraints, maintainability, and available free-tier tools.

# 5. Schedule and Milestones

## 5.1 Twelve-Week Schedule Baseline

Calendar dates below are proposed because the supplied files define W1–W12 but do not provide a formally approved project start date. Week numbers remain authoritative until Eng./Dr. Yasmain ElSharakwy approves calendar dates.

| Week | Proposed dates | Primary work | Required outputs / checkpoint | Owner(s) |
| --- | --- | --- | --- | --- |
| W1 | 19–25 Oct 2026 | Initiation, problem statement, objectives, stakeholder identification, initial risks. | Charter draft, initial stakeholder register, action/risk logs. | Sara; Team Member 2 |
| W2 | 26 Oct–1 Nov 2026 | Scope/MoSCoW baseline, role mapping, tech-stack decision, research start, initial requirements. | M1: Scope baseline approved; D1 management plan submitted for review. | Sara; Team Member 2; Supervisor approves |
| W3 | 2–8 Nov 2026 | Complete requirements, acceptance criteria, core UI flows, data/API contract. | M2: Requirements and core design approved; D2. | Team Members 2, 3, 5; Supervisor approves |
| W4 | 9–15 Nov 2026 | Finish wireframes and data design; repository/environment setup; begin account/profile screens. | D3 UI/UX prototype and data model accepted for build. | Team Members 3, 4, 5 |
| W5 | 16–22 Nov 2026 | Sprint 1: registration, roles, profiles, privacy foundations; begin incremental tests. | Account/profile module and early test cases. | Team Members 4, 5, 6 |
| W6 | 23–29 Nov 2026 | Sprint 2: athlete/professional search, filters, directories; prepare synthetic data. | Search module in progress; test data populated. | Team Members 4, 5; QA |
| W7 | 30 Nov–6 Dec 2026 | Complete search and opportunity listing workflows; integrate frontend/backend weekly. | Search/listing acceptance checks and integrated candidate build. | Team Members 4, 5, 6 |
| W8 | 7–13 Dec 2026 | Sprint 3: connection requests as approved, admin moderation, verification labels, integration. | M3: Must-have feature set runs end-to-end; D4 candidate MVP. | Team Members 4, 5, 6; Sara coordinates |
| W9 | 14–20 Dec 2026 | Formal functional/system testing, responsive checks, usability sessions, risk review. | Test evidence, usability observations, prioritised defects. | Team Member 6; Team Member 2 |
| W10 | 21–27 Dec 2026 | Defect correction, regression, privacy/security review, KPI calculations. | M4: Testing completed; D5 report; zero open critical defects required. | Team Member 6 and developers |
| W11 | 28 Dec 2026–3 Jan 2027 | Buffer/contingency week for approved fixes, environment problems, report reconciliation, final review. | Recovery from slippage; no new optional scope; final document draft and demo backup. | Sara; all owners as required |
| W12 | 4–10 Jan 2027 | Final rehearsal, report/slides finalisation, sign-off, submission and handover. | M5: D6 and final delivery; demonstrable local/recorded demo. | Sara; Team Member 2; Supervisor approves |

## 5.2 Milestone Register

| Milestone | Target | Entry criteria / dependencies | Completion criteria | Accountable approver |
| --- | --- | --- | --- | --- |
| M1 — Scope baseline approved | End W2 — 1 Nov 2026 | Initial charter, user groups, feature list, risk scoring, role mapping decisions presented. | Objectives, users, exclusions, MoSCoW and priority conflict resolutions are recorded and approved. | Eng./Dr. Yasmain ElSharakwy |
| M2 — Requirements and core design approved | End W3 — 8 Nov 2026 | Research/requirements draft and core user journeys available. | Requirements include testable acceptance criteria; role design/API contract and core screens are reviewed. | Eng./Dr. Yasmain ElSharakwy |
| M3 — Must-have features complete | End W8 — 13 Dec 2026 | Approved design, account/profile and search/listing components integrated. | All agreed Must features run end-to-end in test environment; sample data and known limitations documented. | Eng./Dr. Yasmain ElSharakwy |
| M4 — Testing completed | End W10 — 27 Dec 2026 | Integrated MVP and test set available. | Results recorded; no unresolved critical defects; remaining non-critical defects are prioritised and disclosed. | Eng./Dr. Yasmain ElSharakwy |
| M5 — Final delivery | End W12 — 10 Jan 2027 | Final report, presentation, demo build and backup prepared. | Prototype, report and slides submitted; demo rehearsed; handover and approval record completed. | Eng./Dr. Yasmain ElSharakwy |

## 5.3 Schedule Control and Status Definitions

| Status | Definition and required response |
| --- | --- |
| Not started | Work has not begun; an owner and due date are recorded. |
| In progress | Work has begun and evidence is being captured. |
| At risk | A likely delay, quality gap, or dependency threatens the planned date; owner provides a recovery action. |
| Blocked | Work cannot continue until an obstacle or decision is resolved; escalate to Sara immediately. |
| Complete | Output exists and completion evidence is available; acceptance may still be pending. |
| Accepted | The named approver has confirmed that the output meets the agreed criteria. |

## 5.4 Gantt-at-a-Glance

Legend: ● primary activity; ○ continuous or supporting activity; B buffer/contingency focus.

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning / scope baseline | ● | ● |  |  |  |  |  |  |  |  |  |  |
| Requirements / acceptance |  | ● | ● |  |  |  |  |  |  |  |  |  |
| UI/UX / data model |  |  | ● | ● |  |  |  |  |  |  |  |  |
| Sprint 1 — accounts/roles/profiles |  |  |  | ● | ● |  |  |  |  |  |  |  |
| Sprint 2 — search/directories/opportunities |  |  |  |  |  | ● | ● |  |  |  |  |  |
| Sprint 3 — networking/admin/privacy |  |  |  |  |  |  |  | ● |  |  |  |  |
| Incremental tests and integration |  |  |  |  | ○ | ○ | ○ | ○ |  |  |  |  |
| System/responsive/usability testing |  |  |  |  |  |  |  |  | ● | ● |  |  |
| Defect fixing / regression |  |  |  |  |  |  |  |  | ● | ● | ○ |  |
| Buffer / contingency |  |  |  |  |  |  |  |  |  |  | B |  |
| Documentation (continuous; finalised at end) | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ○ | ● | ● |
| Final rehearsal / presentation / delivery |  |  |  |  |  |  |  |  |  |  | ○ | ● |

# 6. Team Structure and Responsibilities

## 6.1 Team Roles

| Team role | Assigned person | Core responsibilities | Backup / coverage |
| --- | --- | --- | --- |
| Project Manager / Team Lead | Sara Abdulwahab | Schedule, milestones, meetings, task allocation, scope/change control, risk review, progress reporting, escalation, supervisor communication, final delivery. | Business Analyst/Documentation Lead supports status reporting; developers provide evidence directly. |
| Business Analyst and Documentation Lead | Team Member 2 — personal name not stated in supplied sources | Stakeholder needs, requirements, user stories/use cases, acceptance criteria, references, decision log, final report, slides and submission package. | Sara Abdulwahab reviews and covers essential documentation if the member is unavailable. |
| UI/UX Designer | Team Member 3 — personal name not stated in supplied sources | User journeys, wireframes, responsive layouts, usability rationale, accessibility checks, visual consistency. | Frontend Developer supports layout adjustments. |
| Frontend Developer | Team Member 4 — personal name not stated in supplied sources | Responsive screens, forms, search/results interfaces, status display, client-side validation, frontend integration. | Backend Developer assists with integration; QA Lead may support early frontend tasks if needed. |
| Backend Developer | Team Member 5 — personal name not stated in supplied sources | Data model, authentication, role permissions, profiles, search logic, opportunities, privacy, backup and setup instructions. | Frontend Developer assists with integration; task notes must enable handover. |
| QA / Testing Lead | Team Member 6 — personal name not stated in supplied sources | Test strategy, functional/system/regression tests, defect log, responsive/security/privacy checks, usability sessions, KPI calculations. | Developers retest their fixes; QA remains the independent verifier of acceptance. |
| Supervisor / Official Approver | Eng./Dr. Yasmain ElSharakwy | Approves scope and major changes, reviews milestones, provides academic direction, accepts deliverables and final project. | No alternate approver is defined in the supplied instructions. |
| Optional sports-domain adviser | Not assigned | Reviews terminology and sports workflows if available and approved. | Not a dependency for core delivery. |

If the team has only five available members, Sara also covers Business Analysis and Documentation; developers share defect fixing; and the QA Lead may support frontend work in Sprint 1–2. The six-member plan remains the working assumption until the kickoff confirms the actual headcount.

## 6.2 RACI Matrix

R = Responsible for performing the work; A = Accountable for the final outcome; C = Consulted; I = Informed. Each row has exactly one A. Supervisor accountability is reserved for academic approval, scope approval, and final acceptance; Sara is accountable for day-to-day project control and work coordination.

| Activity | Sara / PM | BA / Docs | UI/UX | Frontend | Backend | QA Lead | Eng./Dr. Yasmain ElSharakwy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Approve project charter and scope baseline | R | C | I | C | C | I | A |
| Gather stakeholder needs and research | C | A/R | C | I | I | C | I |
| Define requirement acceptance criteria | C | A/R | C | C | C | C | I |
| Confirm role mapping and MoSCoW conflicts | R | C | I | C | C | C | A |
| Design UI/UX and user journeys | C | C | A/R | C | C | C | I |
| Design data model/API contract | C | C | C | C | A/R | C | I |
| Develop frontend | C | I | C | A/R | C | C | I |
| Develop backend/authentication/privacy | C | C | I | C | A/R | C | I |
| Plan and execute verification | C | C | C | C | C | A/R | I |
| Fix defects and run regression | C | I | C | R | R | A | I |
| Manage risk register and escalations | A/R | C | C | C | C | C | I |
| Approve significant change request | R | C | C | C | C | C | A |
| Prepare final report and presentation | A | R | C | C | C | C | I |
| Approve milestone deliverables | R | C | C | C | C | C | A |
| Accept final project and closure | R | C | C | C | C | C | A |

# 7. Communication and Meeting Plan

## 7.1 Communication Cadence

| Communication | Audience | Frequency / timing | Channel | Owner and record |
| --- | --- | --- | --- | --- |
| Team meeting | All six team members | Weekly; additional meeting near a milestone or blocker | Agreed online/in-person meeting | Sara; minutes and action log |
| Short check-in | All team members | 2–3 times per week | Team chat | All members; blockers copied into issue log |
| Sprint planning/review | Team, with supervisor invited at gates | End of each sprint / at W2, W3, W8, W10, W12 gates | Demo/review meeting | Sara; decision log and acceptance notes |
| Supervisor update | Eng./Dr. Yasmain ElSharakwy | Every 1–2 weeks and at each milestone | Email or agreed meeting channel | Sara; dated status report |
| Risk review | Team, led by PM | Weekly | Risk register review | Sara; scores/actions updated |
| Technical integration | Frontend, Backend, UI/UX, QA | Weekly at minimum; more often during integration | Repository issue/PR review | Technical owners; merged PRs and integration notes |
| Critical escalation | Sara and relevant owner; supervisor if scope/safety/deadline impact | Immediately after identification | Agreed urgent channel, followed by written record | Person raising issue; issue log updated by Sara |
| Deliverable approval | Supervisor and deliverable owner | At M1–M5 | Review session or written approval | Sara; approval evidence saved |

## 7.2 Meeting Rules

- Circulate the agenda and any demo link before the meeting where possible; keep routine check-ins focused on progress, blockers, next actions, owners and due dates.

- Record decisions, rejected options, change requests, and action items in the shared project folder within 24 hours.

- Escalate any likely milestone miss, security/privacy issue, or blocked cross-team dependency as soon as it is recognised; do not wait for the next weekly meeting.

- No change to committed scope or milestone dates is considered approved until Eng./Dr. Yasmain ElSharakwy's decision is recorded.

- Keep user research evidence anonymous where possible and do not share personal/under-18 data through informal chat channels.

## 7.3 Escalation Path

| Level | Trigger | Required action | Decision authority |
| --- | --- | --- | --- |
| 1 — Task level | A task is blocked within one workstream for more than one working day. | Owner records the blocker, impact, attempted fix, and support needed; notify Sara. | Sara coordinates the recovery. |
| 2 — Cross-team / schedule | Integration failure, likely milestone slippage, material quality risk, or member capacity issue. | Sara convenes the relevant owners, defines options and dates, updates risks/issues, and informs supervisor if baseline is threatened. | Sara for task sequencing; Eng./Dr. Yasmain ElSharakwy for changes to scope/approval. |
| 3 — Security, privacy, safeguarding, or major baseline threat | Suspected data exposure, under-18 privacy breach, unauthorised access, or likely failure of delivery. | Stop or disable the affected workflow, preserve evidence without spreading personal data, notify Sara and supervisor immediately, document a safe corrective plan. | Eng./Dr. Yasmain ElSharakwy directs academic approval; technical owner implements approved fix. |

# 8. Risk Management and Mitigation

## 8.1 Risk Scoring Method

Risk score = Probability (P, 1–5) × Impact (I, 1–5). The thresholds are planning values from the SportSphere plan and should be confirmed by the supervisor: Low = 1–5; Medium = 6–12; High = 13–25. The register is reviewed weekly and after a material change, incident, failed milestone, or change in participant availability. Scores are estimates, not measured frequencies.

## 8.2 Risk Register R1–R13

| ID | Risk / consequence | P | I | Score / level | Owner | Mitigation / preventive action | Contingency if risk occurs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Development delays threaten the fixed Week 12 delivery date. | 4 | 5 | 20 — High | Sara Abdulwahab | Use MoSCoW, weekly progress reviews, early integration, named task owners, backup ownership, and W11 buffer. | Remove Could-have work first, then propose a documented Should-have reduction; protect Must/privacy controls and notify Eng./Dr. Yasmain ElSharakwy. |
| R2 | Scope expansion increases complexity and displaces core requirements. | 4 | 4 | 16 — High | Sara Abdulwahab | Maintain approved scope baseline; log every change; evaluate time, quality, risk, and person-hours before implementation. | Freeze new features; supervisor decides approve/reject/defer; update baseline only after approval. |
| R3 | Critical defects are discovered too late for safe correction. | 4 | 4 | 16 — High | Team Member 6 — QA Lead | Begin testing in W5; define acceptance criteria early; review each sprint; keep test data and regression cases current. | Use W9–W11 to fix and retest; defer optional features; do not declare acceptance with open critical defects. |
| R4 | Unauthorised access or data exposure occurs. | 3 | 5 | 15 — High | Team Member 5 — Backend Developer | Use hashed passwords, strict role checks, secure authentication, test permissions, minimise personal data, and run security checklist. | Disable affected feature/account access, preserve incident record, correct and retest before re-enabling; notify PM/supervisor promptly. |
| R5 | Credentials cannot be verified and profiles make misleading claims. | 3 | 5 | 15 — High | Team Member 2 — Business Analyst | Display Verified/Unverified labels; only an administrator sets status; never describe users as certified without evidence. | Keep profiles Unverified until reviewed; remove misleading wording and correct records. |
| R6 | Under-18 athlete information or contact details are exposed. | 3 | 5 | 15 — High | Team Member 5 — Backend Developer, supported by Team Member 2 | Private by default for under-18s; hide contact details; use consent notice and guardian-consent controls; use synthetic test accounts. | Stop affected exposure, disable the feature, notify PM/supervisor, restrict/remove data, document the fix and verify before restoring service. |
| R7 | Frontend/backend integration conflicts delay the build. | 3 | 4 | 12 — Medium | Team Members 4 and 5 | Agree API contract in W3; use branches and pull requests; integrate weekly; share test payloads and document schema changes. | Reduce integration scope to the agreed MVP contract; pair-debug; record new owner/date and replan immediately. |
| R8 | Low participation in usability testing limits evaluation evidence. | 3 | 4 | 12 — Medium | Team Member 6 — QA Lead, with Team Member 2 | Start recruitment by W5; use short task-based sessions; identify backup participant pools; prepare scenarios in advance. | Run structured scenario-based tests with available participants/team proxies, clearly report sample size and limitation, and avoid unsupported claims. |
| R9 | Empty or unrealistic demo data makes the platform look unfinished. | 4 | 3 | 12 — Medium | Team Member 5 — Backend Developer | Prepare clearly fictional sample profiles/opportunities in Sprint 2; test search queries on the sample set. | Load the tested local seed dataset and clearly identify it as synthetic; use screenshots/recorded demo if appropriate. |
| R10 | Database errors, accidental deletion, or data loss disrupt demonstration. | 3 | 4 | 12 — Medium | Team Member 5 — Backend Developer | Validate data operations; keep versioned schema/seed data; make regular backups and test restore steps. | Restore the most recent known-good backup; document lost/recreated test data; rerun regression tests. |
| R11 | Inappropriate or misleading content undermines user trust. | 3 | 4 | 12 — Medium | Sara Abdulwahab | Define user rules; include report/review pathway; restrict profile claims; use admin moderation and sample-data controls. | Remove or suspend affected content/account under the moderation process; log decision and review prevention. |
| R12 | Team member absence or missed commitments causes work gaps. | 3 | 3 | 9 — Medium | Sara Abdulwahab | Keep tasks documented; identify backup owner for critical modules; use repository and handover notes; check capacity weekly. | Reassign critical tasks to the documented backup; remove optional work and inform supervisor if delivery baseline is at risk. |
| R13 | Hosting or demo environment fails during assessment. | 3 | 3 | 9 — Medium | Sara Abdulwahab | Guarantee a local demo path; maintain a backup copy and recorded demo video; rehearse on the intended equipment. | Switch to the local environment or recorded demo; document any limitation and preserve submission evidence. |

## 8.3 Risk Response Rules

- Mitigation is preventive action taken before a risk materialises; contingency is the predefined response after it occurs.

- Any risk score of 13 or above is High and must have an active owner, a next action, and a visible weekly status.

- A security, privacy, or under-18 safeguarding issue takes precedence over feature completeness. The affected feature remains disabled until corrected and retested.

- When schedule recovery is needed, defer Could-have work before accepting lower quality. Any reduction to Must-have scope needs supervisor approval and a documented exception.

# 9. Issue, Assumption, Dependency, and Decision Logs

These are initial planning records. “Open” means the item needs confirmation or action; it does not claim that an execution incident has already occurred. The logs must be updated throughout delivery.

## 9.1 Issue Log

| ID | Date raised | Issue / impact | Owner | Next action / due | Status |
| --- | --- | --- | --- | --- | --- |
| ISS-01 | 16 Oct 2026 | Source documents contain priority and role-model conflicts (FR-06, FR-12, FR-13, FR-19; five canonical roles versus six account/persona labels). If not resolved, the team may build the wrong acceptance baseline. | Sara Abdulwahab | Present the reconciliation table to Eng./Dr. Yasmain ElSharakwy and record decisions by end W2, 1 Nov 2026. | Open — planning clarification |
| ISS-02 | 16 Oct 2026 | Calendar dates are not approved in the source materials. Inconsistent dates could compromise milestone tracking. | Sara Abdulwahab | Confirm proposed 19 Oct 2026–10 Jan 2027 calendar mapping at kickoff / M1. | Open — planning assumption |
| ISS-03 | 16 Oct 2026 | Individual names for Team Members 2–6 are not given in the supplied source documents. Task ownership needs to be made personal and explicit. | Sara Abdulwahab | Record names, availability, and backups at kickoff before technical work is allocated. | Open — team administration |

## 9.2 Assumption Log

| ID | Assumption | Validation method | Owner | Validate by | Status |
| --- | --- | --- | --- | --- | --- |
| A1 | Final delivery is at the end of W12; scope can flex but the date is fixed. | Obtain supervisor confirmation of week and calendar dates. | Sara Abdulwahab | W1–W2 | Open for confirmation |
| A2 | Each of six members can contribute approximately 8–10 hours per week. | Confirm availability and adjust task allocation. | Sara Abdulwahab | W1 | Open for confirmation |
| A3 | The prototype uses sample/test data only and no real medical or sensitive personal data. | Review seed data and privacy checklist before testing. | Team Member 5 and Team Member 6 | W4, then each release | Accepted planning rule; ongoing compliance |
| A4 | Technology stack is selected in W2 according to team skills and available tooling. | Compare options with team capability and local-demo constraints; record decision. | Team Member 5 with Sara | W2 | Open for decision |
| A5 | A local demo environment is guaranteed; cloud hosting is optional. | Rehearse local setup and restore instructions. | Team Member 5 | W4 and W11 | Open until rehearsal |

## 9.3 Dependency Log

| ID | Dependency | Impact if delayed | Owner | Required by / response | Status |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | Supervisor approval of scope, role mapping, and priority conflicts. | Requirements and development baseline may be unstable. | Sara Abdulwahab | M1, end W2; escalate if unavailable. | Open |
| DEP-02 | Requirements and acceptance criteria approved before core build. | Rework and inconsistent verification. | Team Member 2 | M2, end W3. | Planned |
| DEP-03 | API/data contract agreed by frontend and backend before parallel integration. | Integration delays and incompatible components. | Team Members 4 and 5 | W3; integrate at least weekly. | Planned |
| DEP-04 | Suitable participant access for interviews/usability review. | Usability sample may be smaller than target. | Team Member 2 and Team Member 6 | Recruitment begins W5. | External dependency |
| DEP-05 | Local demo environment, seed data, and backup copy are available. | Failed demonstration or non-reproducible testing. | Team Member 5 | Demo rehearsal by W11. | Planned |
| DEP-06 | Approved free-tier development/design/repository tools remain accessible. | Work may need to migrate or use a local alternative. | Sara and relevant tool owner | Validate W2 and revisit weekly. | Planned |

## 9.4 Decision Log

| ID | Decision / question | Planning position | Decision authority | Due / evidence | Status |
| --- | --- | --- | --- | --- | --- |
| DEC-01 | Project title and scope identity | SportSphere is the project; AthleteConnect is the title of the supplied requirements document whose material is carried over. | Sara; supervisor confirms baseline | D1/M1 | Proposed in v1.0 |
| DEC-02 | Top-level system roles | Use five canonical roles; map scouts to Coach/Staff and sponsor-specific capabilities to specialist permissions unless a sixth top-level role is approved. | Eng./Dr. Yasmain ElSharakwy | End W2 | Pending approval |
| DEC-03 | FR-06 sports video scope | Keep the requirement visible as Must from the requirements source; confirm implementation feasibility and acceptance limits at M1. Video analysis remains out of scope. | Eng./Dr. Yasmain ElSharakwy | End W2 | Pending approval |
| DEC-04 | Networking and notifications priorities | Requests = Should; direct messaging = Could; email notifications = Could, reflecting SportSphere scope baseline over the broader grouping in the requirements document. | Eng./Dr. Yasmain ElSharakwy | End W2 | Pending approval |
| DEC-05 | Tech stack | Select after skills/options review in W2; document reasons, versions, and local-demo setup. | Team, with Sara accountable for coordination; supervisor consulted | End W2 | Open |
| DEC-06 | Under-18 athlete privacy | Private by default, contact details hidden, clear consent/guardian-consent controls, test data only. | Eng./Dr. Yasmain ElSharakwy approves; Backend Developer implements | M1 and before user testing | Proposed safeguard |
| DEC-07 | Demo strategy | Local demo is primary; recorded demo video and backup copy are contingency options. | Sara and Backend Developer | Tested by W11 | Planned |
| DEC-08 | Project calendar | Use the proposed 19 Oct 2026–10 Jan 2027 schedule unless supervisor directs otherwise. | Eng./Dr. Yasmain ElSharakwy | M1 | Pending approval |

# 10. Quality Management and Testing

## 10.1 Quality Plan

| Quality area | Planned activity | Evidence / acceptance threshold | Owner |
| --- | --- | --- | --- |
| Functionality | Test each approved requirement against its acceptance criteria; include positive, negative, and boundary cases as relevant. | At least 95% of executed functional tests pass; all Must requirements have pass evidence or documented supervisor-approved exception. | Team Member 6 — QA Lead |
| Completeness | Cross-check scope, FR/NFR traceability, work products, and report against the approved baseline. | 100% of Must-have requirements traced to a test or justified approved exception. | Team Member 2; Sara reviews |
| Usability | Ask representative participants to complete common tasks; record observation and feedback. | Target 10–15 participants where available; average satisfaction target at least 4/5; limitations disclosed if sample is smaller. | Team Member 2 and QA Lead |
| Responsiveness | Check Must-have pages on phone, tablet, and desktop widths; test in at least two browsers. | 100% of Must-have pages pass the agreed responsive checklist at all three screen sizes. | Team Member 3, Team Member 4, QA Lead |
| Security and privacy | Review authentication, permissions, data minimisation, privacy defaults, minor safeguarding, and moderation. | No known critical security/privacy defect remains at acceptance; all role access tests recorded. | Team Member 5 and QA Lead |
| Data quality | Validate required fields, formats, search filters, sample data and status values. | Invalid required fields are rejected or explained; seed data is clearly synthetic; query expectations are documented. | Team Member 5 and QA Lead |
| Professional information / verification | Show Verified/Unverified status without unsupported certification claims. | 100% of profiles display a status label; only authorised admin action changes verification status. | Team Member 2 and Team Member 5 |
| Code quality | Use version control, feature branches, pull requests, peer review, and documented setup. | Every merged feature reviewed by another team member; critical setup steps documented. | Team Member 5; all developers |
| Maintainability | Document API/data contracts and keep modules reasonably separated. | NFR-12 target: documented APIs and 70% automated test coverage where measurable; unmeasured items reported honestly. | Team Member 5 and QA Lead |
| Documentation / presentation | Compare final report to implemented prototype; proofread tables, figures, references, versions, and limitations. | Final checklist complete; no claim presented as measured without test evidence. | Team Member 2 and Sara |

## 10.2 Definition of Done

A feature is “Done” only when (1) implementation is complete; (2) another member has reviewed it; (3) the acceptance criterion has been tested; (4) it works at the agreed mobile and desktop breakpoints; (5) privacy/role checks relevant to the feature pass; (6) defects and evidence are logged; and (7) the change is merged into the main branch. Completion does not equal acceptance until the authorised reviewer confirms it.

## 10.3 KPI Register

All values are proposed targets. No target may be reported as achieved until it has been measured and the measurement evidence is available.

| KPI | Measurement | Target | Evidence / timing | Owner |
| --- | --- | --- | --- | --- |
| Functional test pass rate | Passed functional tests ÷ executed functional tests × 100 | At least 95% | Test report at W10, with regression updates in W11 if needed. | QA Lead |
| Unresolved critical defects | Count at final evaluation | 0 | Defect register at M4 and M5. | QA Lead and developers |
| Responsive layout checks | Must-have pages passing on mobile, tablet, desktop and at least two browsers | 100% of Must-have pages | Responsive checklist and screenshots by W10. | UI/UX, Frontend, QA |
| Page response time | Median response time for selected pages in defined test environment | 2 seconds or less in the SportSphere KPI; NFR-01 separately targets page load under 3 seconds | Timing record with device/network/test setup by W9–W10. | QA Lead / developers |
| Search latency | Queries completed under 2 seconds ÷ measured queries | At least 95% under 2 seconds | Predefined search test set by W10. | QA Lead / Backend Developer |
| Registration completion | Completed registrations ÷ attempted registrations in test group × 100 | At least 80% | Test session logs; do not use as a production conversion metric. | QA Lead |
| Search success rate | Successful predefined search tasks ÷ total predefined search tasks × 100 | At least 90% | Scenario-based task results. | QA Lead / Research Lead |
| Profile completion rate | Profiles meeting required-field criteria ÷ profiles created × 100 | At least 80% | Seed/test profile audit. | QA Lead |
| Verification status display | Profiles displaying a verification status ÷ all profiles × 100 | 100% | Profile/admin audit. | Backend Developer / QA Lead |
| User satisfaction | Average rating from structured survey | At least 4/5; target 10–15 respondents where available | Survey results and sample size at W10. | Research Lead |
| Scope delivery rate | Completed Must requirements ÷ agreed Must requirements × 100 | 100%, or documented supervisor-approved exceptions | Requirements/test traceability at M4/M5. | Sara and QA Lead |
| Milestone adherence | Milestones met on time ÷ 5 × 100 | At least 4 of 5 milestones | Schedule and approval evidence. | Sara |
| System availability | Available monitoring time ÷ total monitoring time × 100 | 99% only if hosted with a defined pilot period (NFR-10 has a separate 99.5% monthly target) | Hosted monitoring log; omit and explain if local-only. | Sara / Backend Developer |
| Video playback startup | Time from initiating playback to first playable frame | Under 5 seconds if FR-06 is approved and measurable | Representative test media and documented network conditions. | QA Lead / Backend Developer |
| Automated test coverage | Lines/statements covered ÷ total measured by tool | 70% target where supported by selected stack | Coverage report at W10; report gaps if unavailable. | QA Lead / Backend Developer |

## 10.4 Test / Review Record Template and Initial Planned Checks

No tests are marked Passed in this planning document because the supplied sources do not provide execution results. Add dates, tester, version, evidence link, and actual result during execution.

| Test ID | Requirement(s) | Method | Acceptance condition | Initial status / next action |
| --- | --- | --- | --- | --- |
| T-01 | FR-01 | Register/login/reset positive and negative test | Verified email login works; invalid credentials rejected; reset link expires. | Planned — Team Member 6 to execute in W5 and regression-test later. |
| T-02 | FR-02 / NFR-06 | Role/permission matrix test | Each role can access only permitted functions. | Planned — Team Member 6 with Backend Developer. |
| T-03 | FR-03 / FR-04 / FR-07 / NFR-07 | Profile CRUD and privacy test | Required fields validated; under-18 defaults private; contact detail hidden. | Planned — after profile module is integrated. |
| T-04 | FR-08 / FR-09 / NFR-01 / NFR-02 | Search scenarios and timing | Correct filtered results; latency targets calculated on a documented test set. | Planned — W6–W10. |
| T-05 | FR-10 / FR-11 | Listing lifecycle and application status test | Create/edit/close works; application status works if Should-have is retained. | Planned — W7–W9. |
| T-06 | FR-06 / NFR-03 | Video upload/playback check | Only if approved; media starts within five seconds in defined conditions. | Conditional — scope decision required in W2. |
| T-07 | FR-12 / FR-13 | Connection request and alert test | Connection status works if included; direct messages/email only if approved and implemented. | Planned/conditional — test according to approved MoSCoW baseline. |
| T-08 | FR-16 / R5 / R11 | Admin moderation/verification test | Flagged item can be reviewed; status/action permissions work. | Planned — W8–W10. |
| T-09 | FR-19 / NFR-09 / NFR-13 | Responsive/browser check | Must-have pages pass mobile/tablet/desktop; browser coverage recorded. | Planned — W9–W10. |
| T-10 | NFR-05 / NFR-06 / NFR-07 / NFR-11 | Security/privacy/backup review | No known critical issue remains; data handling and backup steps documented. | Planned — W9–W11. |

# 11. Resource and Budget Management

## 11.1 Resource Allocation

| Resource | Purpose | Planned allocation / control | Owner |
| --- | --- | --- | --- |
| Six team members | Requirements, design, development, testing, documentation, presentation. | Planning envelope of 8–10 hours/person/week; approximately 576–720 person-hours across the project, to be confirmed at kickoff. | Sara Abdulwahab |
| UI/UX tool | Wireframes and clickable prototype. | Figma free tier or an equivalent free tool, subject to access and team agreement. | Team Member 3 |
| Development stack | Build web client, application logic, persistence, and tests. | Chosen in W2 based on team skills, maintainability, offline/local demonstration needs, and free-tier access. | Team Member 5 with Team Member 4 |
| Version control | Source history, branches, peer review, backup. | GitHub or an approved equivalent; feature branches and pull requests. | Team Member 5 |
| Task/project tracking | Sprint board, actions, defects, risks, and decisions. | Trello, Jira, Notion, or another team-accessible free-tier board. | Sara Abdulwahab |
| Communication and storage | Team meetings and official records. | Teams/WhatsApp for coordination; a restricted shared drive for official documents and evidence. Avoid storing sensitive data in chat. | Sara and Team Member 2 |
| Test participants | Usability and acceptance feedback. | Target 10–15 athletes/coaches/students if available and ethically recruited; record actual sample. | Team Member 2 and Team Member 6 |
| Test/demo devices | Responsive checks and presentation. | Existing team laptops/phones/tablet access; arrange a backup device or screenshots where physical devices are limited. | Sara / QA Lead |
| Demo environment | Repeatable project demonstration. | Local environment is primary; cloud hosting optional; maintain seed data, backup copy and recorded demo. | Team Member 5 and Sara |
| Supervisor | Academic review and gate approvals. | Review every 1–2 weeks and at each milestone. | Eng./Dr. Yasmain ElSharakwy |

## 11.2 Budget Baseline

The supplied documents do not state an approved monetary budget or vendor quotes. The conservative baseline is therefore zero approved cash spend, using existing equipment, free-tier tools, and the guaranteed local demo assumption. This is a spending-control decision, not a claim that the project has no economic cost.

| Resource / cost item | Quantity | Estimated direct cash cost | Actual cost at plan issue | Source / owner / control |
| --- | --- | --- | --- | --- |
| Team labour (non-cash academic effort) | 576–720 person-hours estimated | EGP 0 cash budget; not valued as paid labour | Not measured | Six team members; effort to be tracked if required by programme. |
| UI/UX and task tracking tools | Free-tier use | EGP 0 planned | Not measured | Use free tier; owner confirms licensing/access in W2. |
| Source repository | One project repository | EGP 0 planned | Not measured | GitHub or equivalent free plan; Team Member 5. |
| Development hardware | Existing team devices | EGP 0 additional purchase authorised | Not measured | Existing equipment assumption; any required purchase needs approval. |
| Local demo environment | One local build | EGP 0 planned | Not measured | Local environment baseline; cloud hosting optional. |
| Printing, transport, or optional cloud hosting | As needed; not committed | Not priced / not authorised | Not measured | Obtain a price and supervisor approval before commitment. |
| Contingency | Not applicable until spend is authorised | EGP 0 currently authorised; revise only with approval | Not measured | Eng./Dr. Yasmain ElSharakwy approves any cash allocation. |
| Total approved direct cash budget |  | EGP 0 authorised at v1.0 | Not yet measured | Any non-zero spend requires a written approval and an updated budget log. |

## 11.3 Budget Management Rules

- Record currency and the date for any estimate before requesting approval.

- Do not commit to spending, purchasing a subscription, or paying for hosting without prior approval from Eng./Dr. Yasmain ElSharakwy.

- Keep receipts or confirmations for approved expenses and compare estimate with actual cost at W10 and closure.

- If a non-free dependency becomes necessary, first evaluate a free/local alternative and its impact on security, delivery, and reproducibility.

# 12. Change Control

Change control protects the fixed 12-week delivery window and the agreed quality/safeguarding requirements.

## 12.1 Change Request Process

- Log the request, requester, reason, date, and affected requirement(s).

- State expected benefit, users affected, and consequence of rejecting/defering the change.

- Assess impacts on scope, person-hours, milestone dates, budget, quality, security/privacy, dependencies, and the R1–R13 risk register.

- Sara recommends approve, reject, or defer and presents material changes to Eng./Dr. Yasmain ElSharakwy.

- Major changes to scope, deliverables, priority, or final dates require supervisor approval before implementation.

- After approval only, update the requirements baseline, WBS, schedule, test plan, risk/issues, and affected team members; record the new version.

- Rejected or deferred requests remain in the log so they are not reintroduced informally.

## 12.2 Change Request Register

| Change ID | Requested change / reason | Impact assessment | Decision / approver | Plan update / status |
| --- | --- | --- | --- | --- |
| CR-01 | Resolve whether FR-06 video upload/playback remains Must, given the mismatch between requirements gathering and SportSphere scope summary. | Potential impact on media storage, performance, security, effort, and testing; no video analysis tools. | Pending decision by Eng./Dr. Yasmain ElSharakwy at M1. | Open clarification; no scope changed at v1.0. |
| CR-02 | Confirm connection request / direct messaging / notification priorities. | Keeping all as Must may threaten schedule; different permission, privacy, and testing needs. | Pending decision by Eng./Dr. Yasmain ElSharakwy at M1. | Proposed baseline is requests Should, direct messages/email Could. |
| CR-03 | Decide whether sponsor is a distinct top-level account role or a specialist capability inside the five-role model. | A sixth role may affect registration, permissions, interfaces, and acceptance tests. | Pending decision by Eng./Dr. Yasmain ElSharakwy by end W2. | Open; no extra top-level role built until decision. |
| CR-04 | Any future request submitted during delivery. | Complete the change-impact assessment at submission time. | No decision until assessed; supervisor approval required for material changes. | Not submitted at issue date. |

# 13. Document and Information Management

## 13.1 Document Management Rules

| Rule | Required practice |
| --- | --- |
| Official source of truth | Keep the latest approved documents in one restricted shared project folder; repository is the source of truth for code. Avoid uncontrolled parallel copies. |
| Folder structure | 01_Charter; 02_Planning; 03_Research_Requirements; 04_Design; 05_Development; 06_Testing; 07_Meetings_Logs; 08_Final_Submission; 09_Backups. |
| File naming | YYYY-MM-DD_SportSphere_DocumentName_vX.X (example: 2026-10-16_SportSphere_Project_Management_Plan_v1.0.docx). |
| Versioning | v0.x drafts; v1.0 first formally approved version; v1.1 minor edits; v2.0 major baseline revision. The current v1.0 is a consolidation draft pending approval, not a formally approved baseline. |
| Ownership | Each document has a named role owner who updates it, checks completeness, and identifies the current version. |
| Access/privacy | Restrict access to team and supervisor; do not upload personal/under-18 or confidential data to public folders. Use synthetic data for demos. |
| Backups | Maintain a backup copy of code, seed data, presentation assets, and final documents under the agreed institutional/team rules. Test restoration before the final demo. |
| Approval evidence | Record approver name, date, decision, conditions, and version; written email confirmation is acceptable if the programme permits it. |
| References and copyright | Cite external text, images, data, diagrams, and ideas using the required academic style; do not imply affiliation or product equivalence. |
| AI-assisted work | Validate AI-generated material, protect confidential information, disclose use when required by programme rules, and ensure the team remains responsible for final content. |

## 13.2 Document Register

| Document | Owner | Version | Approval / target date | Storage location |
| --- | --- | --- | --- | --- |
| Project Charter and Proposal | Sara Abdulwahab | v1.0 after approval | Eng./Dr. Yasmain ElSharakwy; target M1 | 01_Charter |
| Project Management Plan | Sara Abdulwahab | v1.0 draft at 16 Oct 2026 | Pending supervisor approval; target M1 | 02_Planning |
| Requirements and Traceability Matrix | Team Member 2 | v1.0 target | Eng./Dr. Yasmain ElSharakwy; target M2 | 03_Research_Requirements |
| UI/UX Prototype and Data/API Model | Team Member 3 / Team Member 5 | v1.0 target | Supervisor review at M2 and D3 | 04_Design |
| WBS, Schedule and Action Tracker | Sara Abdulwahab | v1.0 target; updated weekly | Supervisor confirms calendar baseline at M1 | 02_Planning and task board |
| Risk / Issue / Decision / Change Logs | Sara Abdulwahab | v1.0, updated weekly | Review at weekly check-in | 07_Meetings_Logs |
| Source Code and Setup Instructions | Team Member 5 | Repository release tag at M5 | Supervisor demo/acceptance | 05_Development and source repository |
| Test Plan / Results / Defect Log | Team Member 6 | v1.0 target | Supervisor at M4 | 06_Testing |
| Final Report and Presentation | Team Member 2 / Sara | v1.0 final package | Eng./Dr. Yasmain ElSharakwy at M5 | 08_Final_Submission |
| Recorded Demo and Recovery Copy | Sara / Team Member 5 | Final version at W11 | Rehearsed before M5 | 09_Backups and final submission folder |

# 14. Progress Monitoring and Reporting

## 14.1 Reporting Approach

Sara prepares a short weekly status update comparing actual outputs with the approved plan. Report only work supported by evidence: merged code, a reviewed requirement, a test record, meeting decision, or an accepted deliverable. Each material variance gets an explanation, owner, corrective action, and due date.

## 14.2 Initial Status Report at Plan Issue

| Status-report field | Current entry as at 16 October 2026 |
| --- | --- |
| Reporting period | Planning baseline consolidation; no execution period has yet been verified from the source documents. |
| Overall status | Amber — planning draft pending supervisor approval. This is a baseline-readiness status, not a claim of development delay. |
| Completed this period | Consolidated charter structure, scope boundaries, requirements traceability, WBS, proposed 12-week schedule, role mapping proposal, initial risk/log structure. |
| Next priorities | Confirm Team Member 2–6 names and availability; approve scope and priority conflicts; choose stack; approve requirement acceptance criteria; start detailed UI/data design. |
| Schedule / budget variance | Calendar mapping is proposed, not approved; actual effort/spend not recorded. Approved cash budget at v1.0 is EGP 0. |
| Top risks / issues | R1 development delays; R2 scope expansion; R3 late critical defects; R4 unauthorised access/data exposure; R6 under-18 privacy; ISS-01 priority/role conflict. |
| Decisions / support needed | Supervisor approval of calendar dates, role model, FR-06 video scope, networking/notification priority, and technology-selection approach. |
| Evidence location | Official project folder as established under Section 13; insert the actual shared-folder link after the team creates it. |

## 14.3 Weekly Reporting Fields

| Field | Required update |
| --- | --- |
| Reporting week and dates | W1–W12 plus actual date range. |
| Overall status | Green = on track; Amber = needs attention; Red = major risk to delivery. Include reason. |
| Outputs completed | Deliverable/task, evidence link, acceptance status, and reviewer. |
| Next-week priorities | Specific action, owner, due date, priority, dependency, and expected evidence. |
| Schedule/resource variance | Planned versus actual start/finish and effort; explain material differences. |
| Top risks/issues | Current score, owner, response, due date, and escalation status. |
| Decisions needed | Specific decision, requested approver, impact of delay, and decision deadline. |
| KPI updates | Measured numerator/denominator, date, environment, sample size, result, and target. |

## 14.4 Escalation Rule

If a milestone is likely to be missed, notify the team and Eng./Dr. Yasmain ElSharakwy as soon as the impact is known. Include (a) work affected, (b) cause and evidence, (c) impact on scope/date/quality, (d) recovery options, (e) recommendation, and (f) decision deadline. Do not wait for the next routine meeting when security, privacy, safeguarding, or final-delivery success is threatened.

# 15. Stakeholder and User Engagement

## 15.1 Stakeholder Register and Engagement Strategy

| Stakeholder / group | Needs and concerns | Influence | Interest | Engagement method / timing | Owner |
| --- | --- | --- | --- | --- | --- |
| Athletes | Credible profile, control over visibility, relevant opportunities, safe contact. | Medium | High | Interviews/survey where possible; prototype review and beta task tests in W2–W10. | Team Member 2 |
| Coaches | Efficient athlete discovery, filters, opportunity sharing and recruitment workflows. | High | High | Interviews/workshops, filter scenarios, sprint demos. | Team Member 2 / Sara |
| Clubs / academies | Trusted talent pool, shortlist/contact, trial posts. | High | High | Review listing journey; invite representatives to pilot/useability review where feasible. | Sara / Team Member 2 |
| Scouts / recruitment personnel | Search by sport, position, statistics; reliable profiles. | High | High | Search scenario review; validate shortlist fields; scout capability mapped to Coach/Staff pending role decision. | Team Member 2 |
| Sponsors | Relevant public athlete information and clear offer/response status. | High | Medium | Consult during requirements validation; sponsor capability considered Should-have. | Sara / Team Member 2 |
| Project sponsor / academic authority | Business/academic value, schedule and scope control, budget/resource awareness. | High | High | Milestone reviews, weekly/fortnightly status, approval requests. | Sara; Eng./Dr. Yasmain ElSharakwy approves |
| Project Manager | Clear scope, manageable dependencies, decisions and risk control. | High | High | Daily self-monitoring, weekly plan review, escalations. | Sara Abdulwahab |
| Development and QA team | Clear, testable requirements; stable API; useful test evidence. | Medium | High | Requirements walkthrough, weekly integration and sprint review. | Sara / workstream owners |
| Legal / data-protection adviser | Privacy, consent, safeguarding minors, accurate representations. | High | Medium | Consult at privacy/safeguarding gate before user testing; if no adviser is available, use supervisor/programme guidance and document limitation. | Sara / Team Member 2 |
| Sports federations / regulators | Fair practice, age and eligibility constraints. | Medium | Low | Keep satisfied; consult only if relevant guidance is available and time permits. | Team Member 2 |
| Parents / guardians | Safe handling of minors’ data and contact information. | Low | Medium | Clear consent explanation; guardian consent for under-18 participants/users where applicable. Do not solicit unnecessary personal information. | Team Member 2 / Backend Developer |

## 15.2 Stakeholder Prioritisation

| Engagement category | Stakeholders | Practice |
| --- | --- | --- |
| Manage closely | Athletes, coaches, clubs/academies, scouts, sponsors where relevant, project sponsor/academic supervisor. | Regular input, clear decision points, focused review sessions, feedback acknowledged in requirements/logs. |
| Keep satisfied | Legal/data-protection adviser and relevant sports federations/regulators. | Consult at appropriate gates and demonstrate safeguards and scope boundaries. |
| Keep informed | Development/QA team, parents/guardians, other indirect beneficiaries. | Share relevant decisions, safety/privacy explanations, and progress where needed; avoid oversharing personal data. |

## 15.3 User Research Protocol

Before interviews, surveys, or usability tests, explain the academic purpose, voluntary participation, the information collected, the intended use, and how responses will be stored. Obtain permission according to institutional rules. Collect only information needed for the project. Report sample size and limitations; do not imply that a small convenience sample represents all athletes or clubs.

# 16. Ethics, Data, and Responsible Practice

## 16.1 Privacy and Safeguarding Controls

| Control area | SportSphere rule | Evidence / owner |
| --- | --- | --- |
| Under-18 users | Default athlete profiles to private; hide contact details from public/talent-seeker views; use a clear consent notice and guardian-consent control/process as required. | Permission/privacy tests; Team Member 5 and Team Member 6. |
| Test data | Use synthetic/sample accounts and fictional profiles for development, demo, and public screenshots. No real medical or sensitive personal data in the prototype. | Seed-data review; Team Member 5. |
| Data minimisation | Collect only the profile fields needed for the agreed MVP; avoid collecting identity documents, medical data, exact addresses, or unrelated contact information. | Requirements review; Team Member 2. |
| Access control | Role-based permissions must be checked server-side/on every request; interface hiding alone is not sufficient. | Negative permission tests; Team Member 5 / QA Lead. |
| Consent and withdrawal | Explain participation/data purpose; make consent visible; provide the planned export/delete capability or a documented controlled deletion procedure consistent with the approved prototype. | Consent flow and data-deletion test/evidence; Team Member 2 / Backend Developer. |
| Verification and professional claims | Use Verified/Unverified labels; do not claim that an individual is professionally certified unless a proper verification process and evidence support it. | Admin test and content review; Team Member 2. |
| Moderation and reporting | Provide a basic way for administrators to review flagged content and apply a proportionate action. | FR-16 test evidence; Team Member 5 / QA Lead. |
| Academic integrity | Do not fabricate user research, test outcomes, sources, or measured KPI results. Distinguish planning targets, actual results, assumptions, and limitations. | Review against evidence folder; Sara / Team Member 2. |
| Copyright and attribution | Cite reference platforms, borrowed visual assets, external images, data, and text; obtain permission where required. | Reference audit in final review; Team Member 2. |
| AI-assisted material | Verify technical and factual outputs; do not upload confidential or personal data into tools without permission; disclose AI use if required by the programme. | Final report checklist; Sara. |
| Security incident | Disable affected feature if an exposure or serious vulnerability is suspected; preserve minimal evidence safely, notify PM/supervisor, fix and retest before reactivation. | Incident log and retest record; Backend Developer / Sara. |

## 16.2 Explicit Ethical Boundaries

SportSphere is a professional networking and opportunity-discovery prototype, not a medical service. It does not provide diagnoses, treatment recommendations, emergency services, or clinical monitoring. It does not guarantee employment, selection, sponsorship, or contracts. Health/performance professionals may present their professional specialties, but the prototype must not store clinical records or imply that an “Unverified” individual is credentialed. Under-18 safeguards override public visibility or networking convenience.

# 17. Final Report and Presentation Checklist

Complete each item before final submission; record evidence or a reason for any item not applicable.

| Check | Required confirmation | Owner | Status at plan issue |
| --- | --- | --- | --- |
| ☐ | Problem, beneficiaries, and SMART objective are clear. | Sara | Planned for final review |
| ☐ | Scope, exclusions, requirements, MoSCoW priorities, and acceptance criteria are documented. | Team Member 2 | Baseline draft in this plan; approval pending |
| ☐ | All FR/NFR, user-story, and use-case IDs trace to verification or a documented approved exception. | Team Member 2 / QA Lead | Planned |
| ☐ | Schedule, WBS, milestones, RACI, resources, budget rules, and key decisions are included. | Sara | Included in v1.0; baseline approval pending |
| ☐ | Supervisor decisions on role mapping and priority conflicts are recorded. | Sara | Pending M1 |
| ☐ | Test results, defects, KPI measurements, sample size, and limitations are reported honestly. | QA Lead | To be completed in W9–W10 |
| ☐ | Risk, issue, dependency, and change logs describe actual actions and decisions. | Sara | Initial planning logs populated; update weekly |
| ☐ | Under-18 safeguards and data minimisation are verified. | Backend Developer / QA Lead | Test in W5–W10 |
| ☐ | Final report matches the actual implemented prototype; deferred features are identified. | Team Member 2 / Sara | To be completed in W11–W12 |
| ☐ | References, image attribution, and any required AI-use disclosure comply with programme rules. | Team Member 2 | Final audit W12 |
| ☐ | Source code, setup guide, seed data, and repository access are organised. | Backend Developer | To be completed by W12 |
| ☐ | Local demo and recorded backup have been rehearsed. | Sara / Backend Developer | Rehearsal W11–W12 |
| ☐ | Final files are readable, versioned, and in the agreed submission folder. | Team Member 2 | To be completed W12 |
| ☐ | Eng./Dr. Yasmain ElSharakwy has received the required deliverables and approval request. | Sara | Due M5 |

# 18. Project Closure and Lessons Learned

## 18.1 Closure Plan

Closure records what was actually delivered and accepted, remaining limitations, handover ownership, access, and lessons learned. The entries below are planned closure expectations; they must be replaced with actual evidence during W12 rather than treated as completed results now.

| Closure item | Expected evidence / response | Owner / target |
| --- | --- | --- |
| Final deliverables accepted | D1–D6 acceptance evidence, feedback, and any conditions from supervisor. | Sara; Eng./Dr. Yasmain ElSharakwy; W12 |
| Outstanding items and limitations | List deferred Could/Should features, untested browser combinations, unavailable participant samples, unverified load/uptime claims, and known defects. Assign owner/next step or close as accepted limitation. | QA Lead and Team Member 2; W12 |
| Handover / next steps | Document code setup, environment variables/secrets handling, data schema, seed process, and feasible future enhancements. | Backend Developer; W12 |
| Files and access handed over | Confirm repository and shared-folder permissions for supervisor/required assessors; identify final release tag and document versions. | Sara / Team Member 2; W12 |
| Budget and resources reconciled | Report approved spend versus actual spend; confirm whether cash spend remained at zero. | Sara; W12 |
| Risk/issue/change registers closed or transferred | Mark each item closed, accepted, or transferred to a named future owner. | Sara; W12 |
| Lessons learned captured | Record evidence-based start/stop/continue observations and specific changes for future projects. | All team members, coordinated by Sara; W12 |
| Academic submission confirmed | Record submission timestamp/receipt and any supervisor feedback. | Sara; W12 |

## 18.2 Planned Retrospective Topics

| Prompt | Evidence to capture at closure |
| --- | --- |
| What should the team start, stop, and continue doing? | Specific behaviours or process changes tied to examples from the project. |
| Which assumptions were wrong or needed validation? | Assumption ID, date discovered, resulting change, and impact. |
| What caused the largest delay or rework? | Timeline, defect/issue/change record, root cause, and prevention action. |
| Which project-management tool or process helped most? | Examples from the task board, risk review, version control, test logs, or meeting decisions. |
| What would the team change if it repeated the project? | Prioritised actions for requirements clarity, integration, privacy, testing, documentation, and user recruitment. |
| Which objectives were achieved? | Compare actual KPI results with targets; mark each as achieved, partially achieved, not achieved, or not measured. |

## 18.3 Expected Limitations to Disclose if Applicable

- The application is an academic prototype and is not a commercial-scale production service.

- Local demonstration does not prove public-cloud uptime, 10,000-concurrent-user scalability, or the NFR-10 monthly availability target.

- Sample/test accounts do not establish real-world recruitment or sponsorship outcomes.

- Any unimplemented Could-have or Should-have features, any browser/device combinations not tested, and any small usability sample must be stated explicitly.

- The prototype does not deliver medical services, video analysis, AI performance predictions, payments, native mobile apps, or guaranteed recruitment.

# 19. Weekly Team Action Tracker

The tracker is a planned starting backlog at v1.0. Update the status and evidence link each week. No row below claims completed development work as at the planning issue date.

| Week / date | Action | Owner | Due date | Priority | Status / evidence expected |
| --- | --- | --- | --- | --- | --- |
| W1 — 19–25 Oct | Confirm six-member availability and names; review charter and stakeholder list; create shared folder and task board. | Sara; Team Member 2 | 25 Oct 2026 | High | Planned; team roster, charter draft, folder structure. |
| W2 — 26 Oct–1 Nov | Approve MoSCoW scope, role mapping, FR priority conflicts, tech-stack choice, risk thresholds, and calendar dates. | Sara; all leads; Eng./Dr. Yasmain ElSharakwy approves | 1 Nov 2026 | High | Planned; M1 decision/approval log and D1 review. |
| W3 — 2–8 Nov | Complete requirements traceability, acceptance criteria, core user journeys and API/data contract; hold design review. | Team Member 2; Team Members 3 and 5 | 8 Nov 2026 | High | Planned; D2, M2 review notes and approved decisions. |
| W4 — 9–15 Nov | Complete wireframes/responsive layouts; create repository branches; establish local development/demo setup. | Team Members 3, 4 and 5 | 15 Nov 2026 | High | Planned; D3, repository and setup evidence. |
| W5 — 16–22 Nov | Implement account/profile foundations and privacy defaults; execute early registration and permissions tests; start participant recruitment. | Team Members 4, 5 and 6; Team Member 2 | 22 Nov 2026 | High | Planned; first integrated module, T-01/T-02 evidence, recruitment log. |
| W6 — 23–29 Nov | Build search/filter UI and backend; create synthetic athlete/professional/opportunity data. | Team Members 4 and 5; QA Lead | 29 Nov 2026 | High | Planned; search scenarios and seed-data review. |
| W7 — 30 Nov–6 Dec | Complete opportunity lifecycle and directory integration; run performance and regression checks. | Team Members 4, 5 and 6 | 6 Dec 2026 | High | Planned; integrated search/listing build and defect log. |
| W8 — 7–13 Dec | Add approved connection/admin/moderation functions; verify role permissions; demonstrate Must-have workflow. | Team Members 4, 5 and 6; Sara | 13 Dec 2026 | High | Planned; D4 candidate MVP and M3 acceptance review. |
| W9 — 14–20 Dec | Conduct system/responsive/usability tests; execute participant tasks where available; triage defects. | QA Lead and Team Member 2 | 20 Dec 2026 | High | Planned; test report draft, survey results, defect priority list. |
| W10 — 21–27 Dec | Fix defects, rerun regression, finish privacy/security checks and calculate KPIs. | Developers and QA Lead | 27 Dec 2026 | High | Planned; D5, M4 readiness evidence, critical defect count. |
| W11 — 28 Dec–3 Jan | Use buffer only for critical fixes, schedule recovery, setup/backup rehearsal, and final document consistency. | Sara, Backend Developer, Documentation Lead | 3 Jan 2027 | High | Planned; local backup and recorded demo tested; final draft. |
| W12 — 4–10 Jan | Finalise report/slides, rehearse presentation, hand over repository/files, obtain supervisor acceptance, submit project. | Sara and Team Member 2; all members support | 10 Jan 2027 | High | Planned; D6, signed/recorded acceptance, closure log and submission receipt. |

# 20. Approval and Commitment

Approval confirms that this document is the active project-management baseline. Until signatures or written confirmation are recorded, the plan remains v1.0 pending approval; proposed dates and role/prioritisation decisions must not be represented as formally signed off.

By approving this plan, the team agrees to use it as the current baseline, report progress using evidence, protect privacy and safeguarding requirements, and process scope changes through Section 12. Eng./Dr. Yasmain ElSharakwy is the designated supervisor and official approver for scope, milestone acceptance, major change requests, and final closure.

| Role | Name | Signature / confirmation | Date |
| --- | --- | --- | --- |
| Project Manager / Team Lead | Sara Abdulwahab | Signature / written confirmation pending | Upon formal approval |
| Team representative / Business Analyst & Documentation Lead | Team Member 2 — personal name to be entered by the team at kickoff | Signature / written confirmation pending | Upon formal approval |
| Supervisor / Official Approver | Eng./Dr. Yasmain ElSharakwy | Approval / comments pending | Upon formal approval |

# Appendix A — Recommended Submission Package

| Item | What to submit | Owner / evidence |
| --- | --- | --- |
| 1. Project charter and proposal | Problem, objective, stakeholders, success criteria, assumptions, scope and exclusions. | Sara Abdulwahab; D1. |
| 2. Project management plan | Scope, requirements, WBS, schedule, RACI, communications, quality, risk, resources, change control, document control and closure. | Sara Abdulwahab; this document and approved revisions. |
| 3. Evidence folder | Research, user stories/use cases, meeting minutes, risk/issue/decision logs, design snapshots, test results, screenshots, approvals and user feedback. | Team Member 2 and relevant owners. |
| 4. Final report | Context, requirements, design, implementation, results, limitations, conclusions, recommendations and references. | Team Member 2; reviewed by Sara. |
| 5. Presentation / demonstration | Concise sequence: problem → evidence → solution → validation → impact → limitations → next steps. | Sara and all team members. |
| 6. Source and setup package | Repository, release/version tag, setup guide, sample data, and safe handling of secrets/configuration. | Team Member 5. |
| 7. Testing package | Test cases, results, defect register, regression evidence, responsive/privacy checklist, KPI calculations and participant/sample-size note. | Team Member 6. |
| 8. Closure record | Acceptance, handover, outstanding items, resource reconciliation and lessons learned. | Sara; Section 18. |

# Appendix B — One-Page Project Snapshot

| Field | Snapshot at plan issue (16 October 2026) |
| --- | --- |
| Project / team | SportSphere — Integrated Sports Networking and Talent Development Platform; six-member team; Project Manager Sara Abdulwahab. |
| Supervisor | Eng./Dr. Yasmain ElSharakwy. |
| Problem and target user | Sports profiles, opportunities, and professional contacts are fragmented across multiple sources; primary beneficiaries are athletes, clubs, coaches/staff and other sports professionals. |
| Objective and success measures | Deliver a responsive MVP by proposed W12 (10 January 2027); target ≥95% functional test pass, zero critical open defects, 100% responsive checks for Must-have pages and transparent usability evaluation. |
| Main deliverables | D1 management plan/proposal; D2 requirement specification; D3 UI/UX/data design; D4 functional MVP; D5 test/evaluation report; D6 final report/presentation/handover. |
| Next milestone | M1 — scope baseline approval, proposed end W2 / 1 November 2026. |
| Current status | Amber — consolidated draft awaiting supervisor approval; no measured development/test results are asserted. |
| Top risks | R1 development delays (20 High); R2 scope expansion (16 High); R3 late critical defects (16 High); R4 unauthorised access (15 High); R6 under-18 data exposure (15 High). |
| Key decisions needed | Approve calendar dates; confirm five-role mapping and scout/sponsor treatment; resolve FR-06 video scope; confirm connection/messaging/notification priorities; select technology stack. |
| Budget position | EGP 0 approved cash spend at v1.0; free-tier tools/local demo assumed. Any spending requires advance approval. |
| Official project folder | To be created by the team in the agreed shared drive; enter the actual link after setup. |

# Appendix C — Source Register and Traceability Notes

| Source document | Use in this consolidated plan | Source locations consulted |
| --- | --- | --- |
| Project_Management_Graduation_Project_Management_Plan.pdf | Structure and wording framework for the 20 sections, logs, change control, resource management, progress reporting, ethics, closure, action tracker, approval and appendices. | Entire template, pages 1–11. |
| SportSphere — Project Planning & Management.pdf | Project name, PM, platform/duration, assumptions, problem/objectives, scope and MoSCoW baseline, WBS, Gantt, milestones M1–M5, D1–D6, six-member roles, RACI principles, R1–R13, KPI targets, quality plan, communications, resource assumptions, and lessons learned. | Pages 1–20, especially scope pp. 4–5; WBS/schedule/milestones pp. 6–8; team/RACI pp. 11–12; risks pp. 12–13; KPIs pp. 14–15; quality/communication p. 16; lessons/benchmarking pp. 17–20. |
| AthleteConnect Requirements Gathering.pdf | Stakeholder analysis, US-01–US-10, UC-01–UC-06, functional requirements FR-01–FR-19, NFR-01–NFR-13, consent/minor safeguarding concerns, and acceptance criteria. “AthleteConnect” is treated as a source-artifact name, not the project title. | Stakeholders pp. 3–5; user stories pp. 6–8; use cases pp. 9–10; functional requirements pp. 11–12; non-functional requirements pp. 13–14; summary p. 15. |

## Traceability and Integrity Rule

When the source documents disagree, this plan records the discrepancy and names the proposed resolution. Supervisor decisions must be recorded in the decision/change logs and reflected in the next approved version. Requirements without evidence of implementation or testing remain planned, deferred, untested, or not applicable as explicitly noted; they are never reported as achieved merely because they appear in this plan.